## Backlog
Action ID | Description | Responsible | Deadline | Deadline Revised? | Status | Internal/Supervisor Action
1.1.1 | Request last year's document and files | Danny | 27/09/2024 | FALSE | Completed | Supervisor
1.1.2 | Deciding team roles and informing supervisors | All, Alen | 30/09/2024 | FALSE | Completed | Supervisor
1.1.3 | Explore GitHub files and research more about last year’s robot. Discuss the finding during the next team meeting. | George, Mur, Danny | 30/09/2024 | FALSE | Completed | Supervisor
1.1.4 | Complete in-depth research on potential different design (Vine Robot). Discuss the findings during the next team meeting. | Alen, Maz | 30/09/2024 | FALSE | Completed | Supervisor
1.1.5 | Complete workplace charter document | Maz | 2024-01-10 | FALSE | Completed | Supervisor
2.1.1 | Distribute timesheet documentation to all team members | Maz | 30/09/2024 | FALSE | Completed | Internal
2.1.2 | Review and complete workplace document | All | 2/10/2024 | FALSE | Completed | Internal
2.1.3 | Compile literature review on Vine Robots | Alen, Maz | 03/10/2024 | FALSE | Completed | Internal
2.1.4 | Send email summary of questions discussed during the meeting | Alen | 30/09/2024 | FALSE | Completed | Internal
2.1.5 | Create a temporary sharing folder for file collaboration | Maz | 30/09/2024 | FALSE | Completed | Internal
2.3.1 | Complete draft risk register, add on the workplace document, tagged to supervisors | Danny, Maz | 15/20/2024 | FALSE | Completed | Supervisor
2.3.2 | H&S risk assessment | Mur | 08/10/2024 | FALSE | Completed | Supervisor
2.3.3 | Workplace document review | Simon | 2024-01-11 | FALSE | Completed | Supervisor
2.3.4 | Comparison table for robot arm vs continuum, justify choice of design, report of robot articulation | Maz | 30/10/2024 | FALSE | Completed | Supervisor
2.3.5 | System block diagram, allocation of personnel, Associated project plan | Alen | 08/10/2024 | FALSE | Completed | Supervisor
2.3.6 | When to have the Amentum meeting | All, Alen | 08/10/2024 | FALSE | Completed | Supervisor
2.3.7 | Prepare questions to ask Amentum team, complete an agenda | All | 18/10/2024 | FALSE | Completed | Supervisor
3.3.1 | Remake the system block diagram | Alen | 17/11/2024 | FALSE | Completed | Internal
3.3.2 | Create a lone working chat on teams | George | 11/11/2024 | FALSE | Completed | Internal
3.3.3 | Research on interconnecting dependencies | Alen | 17/11/2024 | FALSE | Completed | Internal
3.3.4 | Update mechatronics slide deck with better science communication | Maz, Geroge | 18/11/2024 | FALSE | Completed | Internal
3.3.5 | Add team to Monday.com board for easier team task tracking | Geroge | 11/11/2024 | FALSE | Completed | Internal
4.1.1 | Create an Amentum questions file for the team | Maz | 14/10/2024 | FALSE | Completed | Internal
4.1.2 | More mechanical simulations | Maz, Geroge | 17/10/2024 | FALSE | Completed | Internal
4.1.3 | Proposal of sensors to use | Danny | 17/10/204 | FALSE | Completed | Internal
4.2.1 | Supervisor Meeting Slide Deck Completion | All | 17/10/2024 | FALSE | Completed | Internal
4.2.2 | Converting actions backlog Word file to Excel | Alen | 17/10/2024 | FALSE | Completed | Internal
4.3.1 | Send design requirement slides and guide | Simon, Paul | 24/10/24 | FALSE | Completed | Supervisor
4.3.2 | Complete Design Requirements and Concept of Operations | Alen, Danny | 21/10/24 | FALSE | Completed | Supervisor
4.3.3 | Find project code | Mur | 24/10/24 | FALSE | Completed | Supervisor
4.3.4 | Send the amentum questions document to Simon | Maz | 21/10/24 | FALSE | Completed | Supervisor
4.3.5 | Budget requirements and distribution through systems | Mur | 30/10/24 | TRUE | Completed | Supervisor
4.3.6 | Force to mass of actuation devices | Mur | 24/10/24 | FALSE | Completed | Supervisor
4.3.7 | Timesheets with an honest appraisal and where the effort is expended. | All | 24/10/24 | FALSE | Completed | Supervisor
5.1.1 | Add discussed scenarios on the ConOps | Alen | 21/20/2024 | FALSE | Completed | Internal
5.1.2 | Send amentum questions once updated | Maz | 22/10/2024 | FALSE | Completed | Internal
5.1.3 | Justify why numbers have been chosen in design requirements for control and power | Mur | 21/10/2024 | FALSE | Completed | Internal
5.1.4 | Sensor System Overview draft | Danny | 24/20/2024 | FALSE | Completed | Internal
5.1.5 | Make improvements on the system diagram | Alen | 23/20/2024 | FALSE | Completed | Internal
5.3.1 | ConOps and Design Requirements Review | Simon | 31/10/2024 | FALSE | Completed | Supervisor
5.3.2 | List of items to buy to be review in the next team meeting | All – Mur | 28/10/2024 | FALSE | Completed | Supervisor
5.3.3 | Review of sensor proposal, make improvements based on meeting | Danny | 29/10/204 | FALSE | Completed | Supervisor
5.3.4 | Testing existing IMU, ToF | Danny | 28/10/2024 | TRUE | Completed | Supervisor
5.3.5 | Review and add to ConOps based on this meeting | Alen | 29/10/2024 | FALSE | Completed | Supervisor
5.3.6 | Starting on locking mechanism design | George, Mur | 31/10/2024 | FALSE | Completed | Supervisor
5.3.7 | Discuss with Chris about Continuum backbone | Maz | 28/10/2024 | FALSE | Completed | Supervisor
6.3.1 | Choosing a lens to be added on the Raspberry Pi Camera Module 3 | Alen | 07/11/2024 | FALSE | Completed | Supervisor
6.3.2 | Test BNO055 to find angular precision | Danny | 07/11/2024 | FALSE | Completed | Supervisor
6.3.3 | Create a slideshow for Amentum showcasing a solution with no budget limitation | Geroge | 11/11/2024 | FALSE | Completed | Supervisor
6.3.4 | Further design on locking mechanism and actuators | Mur | 7/11/2024 | FALSE | Completed | Supervisor
7.2.1 | Make sure Amentum questions documents is up to date | All | 07/11/2024 | FALSE | Completed | Internal
7.2.2 | Cover work documents to be handover to the team | Maz, Danny | 07/11/2024 | FALSE | Completed | Internal
7.3.1 | To send off initial orders of microcontroller and camera | Mur | 11/11/2024 | FALSE | Completed | Supervisor
7.3.2 | Forward Simon final list of Amentum questions | Maz | 07/11/2024 | FALSE | Completed | Supervisor
8.1.1 | List of grant pack tasks so elements can be assigned to different people | Maz | 11/11/2024 | FALSE | Completed | Internal
8.1.2 | Forward Simon the questions again, highlighting important ones | Maz | 11/11/2024 | FALSE | Completed | Internal
8.1.3 | Add slides to Amentum presentation | All | 13/11/2024 | FALSE | Completed | Internal
9.2.1 | System Integration Design | Geroge | 10/12/2024 | FALSE | Completed | Supervisor
9.2.2 | Camera illumination design | Alen | 29/11/2024 | FALSE | Completed | Supervisor
9.2.3 | Formatting and submitting GP document | Alen | 21/11/2024 | FALSE | Completed | Supervisor
10.1.1 | Ask Simon and Paul details on meeting | Maz | 25/11/2024 | FALSE | Completed | Internal
11.2.1 | Making a list for technical points that anyone can pickup | George | 09/10.2024 | FALSE | Completed | Internal
11.3.1 | Order LED Ring | Mur | 06/12/2024 | FALSE | Completed | Supervisor
13.1.1 | Email Matt to use the test rig for camera testing | Alen | 31/01/2025 | FALSE | Completed | Supervisor
13.1.2 | Looking at lab risk assessement | Maz | 31/01/2025 | FALSE | Completed | Supervisor
13.1.3 | Check spring steel thickness | Maz | 2025-02-04 | TRUE | Completed | Supervisor
13.1.4 | Order spring steel | Mur | 11/02/2025 | TRUE | Completed | Supervisor
13.1.5 | Speak with 3D manufacturing team | George | 2025-02-04 | TRUE | Completed | Supervisor
13.2.1 | Add topic lists to action log | Alen | 29/01/2025 | FALSE | Completed | Internal
13.2.2 | Continuum stress analysis | Maz | 21/02/2025 | FALSE | Completed | Internal
13.2.3 | Inching unit design | Mur | 31/01/2025 | FALSE | Completed | Internal
13.2.4 | Sending inching unit to print | Mur | 31/01/2025 | FALSE | Completed | Internal
13.2.5 | Inching unit stress analysis | George | 21/02/2025 | FALSE | Completed | Internal
13.2.6 | Purchase actuators | Mur | 31/01/2025 | FALSE | Completed | Internal
13.2.7 | Design and print new disks for nylon rod | George | 31/01/2025 | FALSE | Completed | Internal
13.2.8 | Testing camera rig servos | Alen | 2025-03-07 | TRUE | Completed | Internal
13.2.9 | Testing camera rig illumination | Alen | 2025-03-07 | TRUE | Completed | Internal
13.2.10 | Testing ranging sensors | Danny | 31/01/2025 | FALSE | Completed | Internal
13.2.11 | Integrating sensor outputs into ROS | Danny | 31/01/2025 | FALSE | Completed | Internal
13.2.12 | Create basic URDF model | Maz | 31/01/2025 | FALSE | Completed | Internal
14.1.1 | Send the inching unit design files | Mur | 04/02/2025 | FALSE | Completed | Internal
14.1.2 | Control algorithm Design – Flow chart, proposal | Alen | 14/02/205 | FALSE | Completed | Internal
14.1.3 | Working out (and documentation) inching unit kinematics | George | 14/02/2025 | FALSE | Completed | Internal
14.1.4 | Backbone simulation completion | Maz | 19/02/2025 | TRUE | Completed | Internal
14.1.5 | Adding relevant files | All | 06/02/2025 | FALSE | Completed | Internal
14.1.6 | IMU integration | Danny | 07/02/2025 | FALSE | Completed | Internal
14.1.7 | PCB breakout design for Raspberry Pi | Mur | 18/02/2025 | FALSE | Completed | Internal
14.3.1 | Send Matt a throughout plan of on-site data acquisition process, timings and tools required | Alen | 2025-03-07 | TRUE | Completed | Supervisor
15.1.1 | Write up continuum control ideas (inc. Euler error) | Maz | 18/02/2025 | FALSE | Completed | Internal
15.1.2 | Send Rib design to Mur | George | 11/02/2025 | FALSE | Completed | Internal
16.1.1 | Send backbone ribs design for 3D printing | Mur | 19/02/2025 | FALSE | Completed | Internal
16.1.2 | Send chassis design for 3D prints | Mur | 19/02/2025 | FALSE | Completed | Internal
16.1.3 | Send PCB Raspberry PI breakout design for printing | Mur | 20/02/2025 | FALSE | Completed | Internal
16.1.4 | Sending Orders sensors and fishing lines | Mur | 21/02/2025 | FALSE | Completed | Internal
16.1.5 | Inching unit URDF design | Geroge | 2025-03-04 | TRUE | Completed | Internal
16.3.1 | Testing feet and actuators | Mur | 25/03/2025 | TRUE | Completed | Supervisor
17.1.2 | Motor control (pinout proposal) | Mur, Danny | 06/03/2025 | FALSE | Completed | Internal
17.2.1 | Implement manual control to URDF | George | 06/03/2025 | FALSE | Completed | Internal
17.2.2 | Transfer code to ROS2 | Maz | 07/03/2025 | FALSE | Completed | Internal
18.1.1 | Look at how to do ros2_control of camera | Alen | 12/03/2025 | FALSE | Completed | Internal
18.1.2 | Plan sensor fusion | Danny, George | 11/03/2025 | FALSE | Completed | Internal
18.1.3 | Finalise and send sensor and piPico PCB | Danny, Mur | 06/03/2025 | FALSE | Completed | Internal
18.1.4 | Send Mur Chris’ email | Maz | 05/03/2025 | FALSE | Completed | Internal
18.2.1 | Write up of motor control proposal | Mur, Danny | 11/03/2025 | FALSE | Completed | Internal
18.3.1 | Request new meeting time for the rest of the semester | Maz - All | 10/03/2025 | FALSE | Completed | Supervisor
19.1.1 | Upload sensor visualisation code | Danny | 11/03/2025 | FALSE | Completed | Internal
19.1.2 | Add sensor code to node and topic diagram | Maz | 13/03/2025 | FALSE | Completed | Internal
19.2.1 | Plan to gather dataset for ROS2 | Danny | 17/03/2025 | FALSE | Completed | Internal
19.2.2 | Check how is best to buy train tickets for 18/3 | Mur | 13/03/2025 | FALSE | Completed | Internal
19.2.3 | Check re security clearance timings | Alen | 13/03/2025 | FALSE | Completed | Internal
19.2.4 | Upload motor code to github | Mur | 14/03/2025 | FALSE | Completed | Internal
19.2.5 | Work out how to route cables on continuum | Maz, George | 20/03/2025 | FALSE | Completed | Internal
19.2.6 | Work out where on inching chassis motor and tendons are going | Maz, George | 20/03/2025 | FALSE | Completed | Internal
19.3.1 | Risk Assessment for on-site tests | Alen | 17/03/2025 | FALSE | Completed | Supervisor
19.3.2 | Create a time plan the rest of the tasks remaining | Maz | 20/03/2025 | FALSE | Completed | Supervisor
20.1.1 | Look at geometric limits of combined robot | George, Maz | 20/03/2025 | FALSE | Completed | Internal
20.1.2 | Look to see if we can use microservos on camera system | Alen | 24/03/2025 | FALSE | Completed | Internal
20.2.1 | Upload sensor code on GitHub | Danny | 21/03/2025 | FALSE | Completed | Internal
20.2.2 | Upload most recent CAD files | Mur | 21/03/2025 | FALSE | Completed | Internal
20.3.1 | Coordinate a meeting time with matt for meeting on the 4th of April | Alen | 28/03/2025 | FALSE | Completed | Supervisor
21.1.1 | Editing turning mechanisms proposal | Maz | 28/03/2025 | FALSE | Completed | Internal
21.1.2 | Testing new microservo design | Alen | 28/03/2025 | FALSE | Completed | Internal
21.1.3 | Gather data for current sensors and load sensor | Danny, Mur | 03/04/2025 | TRUE | Completed | Internal
21.1.4 | SolidWork models for turning mechanism | George | 28/03/2025 | FALSE | Completed | Internal
21.2.1 | Final Report parts allocations | Maz | 01/04/2025 | FALSE | Completed | Internal
21.2.2 | Check Docker compatibility with the system | Alen | 01/04/2025 | FALSE | Completed | Internal
22.1.1 | Continuum geometrics rerun | Maz | 04/04/2025 | FALSE | Completed | Internal
22.1.2 | 3DOF geometrics rerun | George | 04/04/2025 | FALSE | Completed | Internal
22.1.3 | Redo code to directly interface with sensor data (all on the same PiPico) | Maz | 07/04/2025 | FALSE | Completed | Internal
22.1.4 | Add pin constants file to code structure | Maz | 01/04/2025 | FALSE | Completed | Internal
22.1.5 | Migrate final report over to LATeX | George | 02/04/2025 | FALSE | Completed | Internal
22.1.6 | Create framework to pick turning mechanism | Maz (George) | 04/04/2025 | FALSE | Completed | Internal
22.3.1 | Making an excel sheet for mitigating risks for the robot | Alen | 05/05/2025 | TRUE | Completed | Supervisor
22.3.2 | Risk analysis of full system | Maz (all) | 18/04/2025 | FALSE | Completed | Supervisor
23.2.1 | Creation of a document for fixes and comments for FR | Maz | 2025-05-01 | FALSE | Completed | Internal
23.3.1 | Write up of the reasonings on 2 prototypes and when each is advantageous | Maz, George | 2025-05-07 | FALSE | Completed | Supervisor
23.3.1 | Bring stepped driver and maxon motor to lab | Paul | 2025-05-05 | FALSE | Completed | Supervisor
24.2.1 | FR excel sheet for final tasks to be completed | Alen | 2025-05-08 | FALSE | Completed | Internal
24.2.2 | FR execl sheet for formatting criteria | Alen | 2025-05-08 | FALSE | Completed | Internal
24.2.3 | Check and carry out tasks of FR excel sheet on report changes | Alen (all) | 2025-05-11 | FALSE | Completed | Internal
24.2.4 | Do checklist tasks for FR formatting | George, Mur | 2025-05-12 | FALSE | Completed | Internal

## Control Tasks
Task ID | Task Description | Responsible | Status
1.1 | Creating and implementing Geolocation |  | Ongoing
2.1 | GUI setup |  | Ongoing
2.2 | Camera Window |  | Ongoing
2.3 | Crack Detection Toggle |  | Ongoing
2.4 | Geolocation |  | Ongoing
2.5 | Visualisation (ideal) |  | Ongoing
3.1 | Design Control Algorithm |  | Ongoing
3.2 | Program Control Algorithm |  | Ongoing
4.1 | Build / Purchase HRI |  | Ongoing
4.2 | Get Physical Controller |  | Ongoing
4.3 | Plan Interactions |  | Ongoing
4.4 | Program Interactions |  | Ongoing
5.1 | Test Control System on ROS2 |  | Ongoing
6.1 | Impletent + test control on real robot |  | Ongoing

## Power Tasks
Task ID | Task Description | Responsible | Status
Completed
Ongoing

## Sensors Tasks
Task ID | Task Description | Responsible | Status
Completed
Ongoing

## Mechatronics Tasks
Task ID | Task Description | Responsible | Status
Completed
Ongoing