## Sheet1
2025-04-28 | 2025-04-29 | 2025-04-30 | 2025-05-01 | 2025-05-02 | 2025-05-03 | 2025-05-04
Team meet to plan week |  |  | Team meet to plan 2/5 meeting and discuss FR | Supervisor meet
2025-05-05 | 2025-05-06 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-10 | 2025-05-11
Team meet to plan week |  | Final draft of FR (bar test data) due | Team meet to plan 9/5 meeting and discuss FR | Supervisor meet Last day for FR test data | Add all test data to FR, all review report | Edits to FR based on review. FR done.
2025-05-12 | 2025-05-13 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-17 | 2025-05-18
FR DUE Alen + Danny exam | Maz exam | Plan video and poster (allocate roles) (online?) | Info needed for demo documented + shared | George exam
2025-05-19 | 2025-05-20 | 2025-05-21 | 2025-05-22 | 2025-05-23 | 2025-05-24 | 2025-05-25
Check in on deliverables, start planning demo |  | Mur exam |  | Full 1st draft of video and poster | All review video and poster
2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-05-29 | 2025-05-30 | 2025-05-31 | 2025-06-01
Meet to discuss video and poster |  | Meet to finalise demo plan, m + h plan |  | VIDEO AND POSTER DUE Last day for sys. changes |  | m + h full draft
2025-06-02 | 2025-06-03 | 2025-06-04 | 2025-06-05 | 2025-06-06 | 2025-06-07 | 2025-06-08
demo day practice day |  | DEMO DAY | meet to check m+h (online?) | M + H REPORT DUE